## sprint 1
SPRINT 1
| total hours |  | 46 | Release 1 - Basic Functionality
days | total estimated hours left | estimated hours completed | expected hours completed | Date | Notes
1 | 46 | 2 | 46 | 2017-08-28 | First Django Application Implementation (actually 23/08/2017)
2 | 44 |  | 44.2 | 2017-08-29
3 | 44 |  | 42.4 | 2017-08-30
4 | 44 |  | 40.6 | 2017-08-31
5 | 44 |  | 38.8 | 2017-09-01
6 | 44 |  | 37 | 2017-09-02
7 | 44 |  | 35.2 | 2017-09-03
8 | 44 |  | 33.4 | 2017-09-04
9 | 44 |  | 31.6 | 2017-09-05
10 | 44 | 2 | 29.8 | 2017-09-06 | Database design drafted
11 | 42 | 1 | 28 | 2017-09-07 | First Django Database implementation
12 | 41 |  | 26.2 | 2017-09-08
13 | 41 |  | 24.4 | 2017-09-09
14 | 41 | 4 | 22.6 | 2017-09-10 | Log in, Register UI Designs finished
15 | 37 | 2 | 20.8 | 2017-09-11 | CSS Stylesheet finalised
16 | 35 |  | 19 | 2017-09-12
17 | 35 |  | 17.2 | 2017-09-13
18 | 35 |  | 15.4 | 2017-09-14
19 | 35 | 7 | 13.6 | 2017-09-15 | Django superuser created, pages coded to perform admin tasks
20 | 28 | 4 | 11.8 | 2017-09-16 | Acceptance testing (admin)
21 | 24 | 4 | 10 | 2017-09-17 | Official database ERD designed, implemented
22 | 20 | 4.5 | 8.2 | 2017-09-18 | Homepage, Settings designs finished
23 | 15.5 | 2 | 6.4 | 2017-09-19 | HTML implementations added to Django, city-based views working
24 | 13.5 | 5.5 | 4.6 | 2017-09-20 | index page implemented to show all city data
25 | 8 | 6 | 2.8 | 2017-09-21 | Acceptance testing (index)
26 | 2 |  | 1 | 2017-09-22

## sprint 2
SPRINT 2
| total hours |  | 31 | Release 1 - Basic Functionality
days | total estimated hours left | estimated hours completed | expected hours completed | Date | Notes
1 | 31 |  | 31 | 2017-10-05
2 | 31 |  | 29.8 | 2017-10-06
3 | 31 | 4.5 | 28.6 | 2017-10-07 | Front end for data display w/ map API
4 | 26.5 |  | 27.4 | 2017-10-08
5 | 26.5 |  | 26.2 | 2017-10-09
6 | 26.5 | 3 | 25 | 2017-10-10 | front end, UI implemented for search engine
7 | 23.5 | 3.5 | 23.8 | 2017-10-11 | Finished logic for search engine
8 | 20 |  | 22.6 | 2017-10-12
9 | 20 |  | 21.4 | 2017-10-13
10 | 20 |  | 20.2 | 2017-10-14
11 | 20 | 2 | 19 | 2017-10-15 | Finished back end implementation for user registration
12 | 18 | 1 | 17.8 | 2017-10-16 | Finalized user login and implemented password encryption (salt)
13 | 17 | 5 | 16.6 | 2017-10-17 | implemented front and back end logic for edit account functionality
14 | 12 |  | 15.4 | 2017-10-18
15 | 12 | 2 | 14.2 | 2017-10-19 | Changed header tabs based on user type
16 | 10 |  | 13 | 2017-10-20
17 | 10 |  | 11.8 | 2017-10-21
18 | 10 | 2 | 10.6 | 2017-10-22 | Acceptance & Unit Testing for user accounts, password encryption
19 | 8 | 1 | 9.4 | 2017-10-23 | Acceptance & Unit Testing for search bar functionality
20 | 7 | 6 | 8.2 | 2017-10-24 | Acceptance & Unit Testing for index & item pages
21 | 1 | 1 | 7 | 2017-10-25 | Acceptance & Unit Testing for 'other information' based on user type
22 | 0 |  | 5.8 | 2017-10-26
23 | 0 |  | 4.6 | 2017-10-27 | RELEASE 1 FINISHED
24 | 0 |  | 3.4 | 2017-10-28
25 | 0 |  | 2.2 | 2017-10-29
26 | 0 |  | 1 | 2017-10-30

## Release 1
Release 1 - Basic Functionality
Sprint 1
| Story ID | Name | Story Points | Estimated Hrs | Actual Hrs
| 03 | Account Setup | 2 | 6 | 5
| 31 | Account Login | 2 | 4 | 3
| 32 | Admin Register | 4 | 4 | 1.5
| 07 | Edit City Information | 4 | 8 | 5
| 04 | Menu Buttons | 2 | 6 | 2.75
| 08 | Hotel Information for Tourists | 4 | 8 | 5.25
| 09 | College Information for Students | 4 | 2 | 1.5
| 10 | Library Information for Students | 4 | 2 | 1.5
| 11 | Hotel Information for Businessman | 4 | 2 | 1.5
| 12 | Industry Information for Businessman | 4 | 2 | 1.5
| 26 | Restaurant Information | 4 | 2 | 1.5
| Total |  | 38 | 46 | 30
Sprint 2
| Story ID | Name | Story Points | Estimated Hrs | Actual Hrs
| 16 | Search Engine | 2 | 6 | 4.25
| 06 | Access to Other Information | 2 | 3 | 1.75
| 02 | Edit Account Details | 4 | 6 | 5
| 01 | Password Encryption | 4 | 2 | 1.5
| 27 | Park Information | 2 | 8 | 7.5
| 28 | Museum Information | 4 | 2 | 1.5
| 29 | Zoo Information | 4 | 2 | 1.5
| 30 | Mall Information | 4 | 2 | 1.5
| Total |  | 26 | 31 | 24.5
|  | Final Burndown | Story Pts | Est. Hrs | Act. Hrs
|  | Sprint 1 | 64 | 77 | 54.5
|  | Sprint 2 | 26 | 31 | 24.5
|  | Release 1 | 0 | 0 | 0