## Slide 1: User Stories - Smart City Project Ordered by release
IFB299 – Project Design & Development
Unit: IFB299 - Project Design and Development
Group 114
Tutor: Ahmed Shoeb Talukder
Tutorial: 6pm Thursday
Version: 1.3
Date 23/08/2017
n9469010, n9592059, n9617019, n9677542, n9727655

## Slide 2: Release 1
Delivery date: 05 October 2017
Total Story Points: 57
This release will provide a simple web service which the end user can use to view city information. System admins will be able to insert and edit city-based information. Users will be able to search for specific entries. Users will be able to register accounts. Registered users will be given information tailored to their interests. When registering, users will need to provide their demographic from the following choices: Tourist, Student or Businessman.

## Slide 3: Core Site Navigation
Website can be viewed and navigated by unregistered users. System Admins have agency to create and edit info entries. Fully implemented search bar, with ‘other information’ option.

## Slide 4: Menu buttons
As a user, I want the system to contain different menu buttons so that I can easily navigate through the different types of information.
Acceptance Criteria:
A link is provided for each type of information that is available to the user.
Clicking a link shows the list of names, addresses, phone numbers/departments/industry types, and email addresses of the selected types of places in the city.
The menu button ‘City information‘ redirects the user to an additional menu containing the list of the names, addresses, phones, and email addresses of the parks, zoos, museums, malls, and restaurants in the city.
Notes:
Story Points:2
Priority:
M
Story ID: 4

## Slide 5: Search engine
As a user, I want the system to provide a search engine so that I can find information more quickly.
Acceptance Criteria:
A user input field should be provided for the search engine.
Clicking ‘Search‘ should search the system for the key words that the user has inputted.
A list of results should be provided, consisting of all the types of information (e.g. a specific hotel) that has been found.
Notes:
Story Points:4
Priority:
S
Story ID: 16

## Slide 6: Access to other information
As a user, I want to be able to view information related to the other user types so that I can utilise all of the city information if necessary.
Acceptance Criteria:
A button ‘Other information‘ is provided at the bottom of the menu
Clicking ‘Other information‘ should redirect the user to the types of information relating to the other user types.
While viewing the ‘Other information‘, the user can click on one of the items in the list (e.g. ‘Industries‘ or ‘Hotels‘) to access further information (a list of names, addresses, phone numbers, email addresses).
Notes: Information that specifically corresponds to certain users will be the default information that is displayed when using the system. However, the users may change their preferences and view the information related to the other user types, if desired.
Story Points:2
Priority:
M
Story ID: 6

## Slide 7: Edit city information
As a user, I want the city information to be updated regularly so that I can avoid relying on outdated or false information.
Acceptance Criteria:
A link ‘Edit information‘ is displayed for Administrators for each type of information.
Clicking ‘Edit information‘ displays the information in an editable format, allowing Administrators to modify all the separate information that is provided in the system.
Clicking on “Save changes“ link should update the city information.
Clicking on “Cancel“ link should redirect the administrator to their previous page and revert any changes.
Notes:
Story Points:4
Priority:
M
Story ID: 7

## Slide 8: Admin Register
As a user, I want the system’s information to be monitored and updated by administrators so that I have access to current, curated recommendations.
Acceptance Criteria:
An ‘Administrator‘ user account can be created using a separate web page.
User type ‘Administrator‘ can create and modify all the data for each city.
Notes:
Story Points:4
Priority:
M
Story ID: 31

## Slide 9: User Functionality
Users can register accounts using web application. To register, users provide usernames, passwords and demographics. User passwords are encrypted in database storage. Registered users can edit their details using the website.

## Slide 10: Account setup
As a user, I want to create a unique account so that I can log into the system.
Acceptance Criteria:
A ‘Register‘ button is displayed.
Clicking ‘Register‘ redirects the user to a page that contains compulsory user input fields for the user‘s name, unique username, and password, as well as optional user input fields for the user‘s phone number, email address and residential address).
The system stores all the account information into a database.
  Notes:
Story Points:2
Priority:
M
Story ID: 3

## Slide 11: Account Login
As a user, I want to log in to my unique account so that I can access the account-specific features of this service.
Acceptance Criteria:
A ‘Log in‘ button is displayed.
Clicking ‘Log in‘ displays two user input fields for the user‘s username and password.
The log-in display has another ‘Log in‘ button, which when clicked should permit the user to enter the system, as long as the username and password are valid.
The system stores all the account information into a database.
  Notes: There may be an option for existing users to log-in automatically, by giving their permission for the website to remember their log-in details. In this case, the user can immediately proceed to viewing the city information.
Story Points:2
Priority:
M
Story ID: 31

## Slide 12: Edit account details
As a user, I want to be able to edit my account details so that I can ensure that my information is kept up-to-date.
Acceptance Criteria:
A link “Edit account“ is displayed when the user is logged in.
Clicking on the “Edit account“ link redirects the user to a new page that displays the user‘s current email address, phone number, and residential address in separate user input fields.
Clicking on a user input field deletes the user‘s previously entered information, and allow the user to input their new details.
Clicking on the “Save changes“ link updates the user‘s account details.
Clicking on the “Cancel“ link redirects the user to their previous page and revert any changes.
All account information is stored in a database, and is updated whenever the user edits their account.
Notes:
Story Points:4
Priority:
M
Story ID: 2

## Slide 13: Password encryption
As a user, I want my password to be encrypted so that I can better protect my account information.
Story Points:1
Priority:
M
Story ID: 1
Acceptance Criteria:
A user input field is provided for the user‘s password.
An asterisk is displayed instead of the user‘s actual input for every character that the user inputs.
The password is be stored into a database.
The password is at least 6 characters
Passwords contains uppercase and lowercase letters, numbers, and special characters.
Notes:

## Slide 14: City-Based Information
Registered or otherwise, users can view city information using the website’s search bar functionality. Basic city information is not recommended to any specific user demographic, and is accessible by all types of users.

## Slide 15: Restaurant information
As a user, I want to be able to view information about restaurants so that I can find the best places to eat in the city.
Acceptance Criteria:
A ‘Restaurants’ link is provided for all users.
Clicking on ‘Restaurants’ displays a list of names, addresses, phone numbers, and email addresses of the restaurants in the city.
The restaurants are displayed on a city map.
Notes:
Story Points:2
Priority:
M
Story ID: 26

## Slide 16: Park information
As a user, I want to browse through information about parks so that I can find the best places for my recreational activities.
Acceptance Criteria:
A ‘Parks’ link is provided for all users, which directs the user to the ‘Parks’ page.
Users can browse through photos of the parks in the city
Clicking a photo displays the name, address, phone number, and email address of the park.
A city map with the locations of the parks is provided.
Notes:
Story Points:2
Priority:
M
Story ID: 27

## Slide 17: Museum information
As a user, I want the system to provide details about museums so that I can admire the exhibitions throughout the city.
Acceptance Criteria:
Users can click on a ‘Museums’ link, which directs the user to ‘Museums’ page.
Users can see the name, address, phone number, and email address for each of the museums in the city.
A city map is provided to pinpoint the locations of each museum in the city.
Users can see a photo of the museum.
Notes:
Story Points:2
Priority:
M
Story ID: 28

## Slide 18: Zoo information
As a user, I want to view information about zoos so that I can find the best establishments for seeing wild animals.
Acceptance Criteria:
Users can click on a ‘Zoos’ link, which directs the users to the ‘Zoos’ page.
Users can see the name, address, phone number, and email address of every zoo in the city.
The system displays a photo of each zoo.
Clicking on ‘Animals’ shows a list of animals that the zoo has on display.
The system provides a map that pinpoints the location of every zoo.
Notes:
Story Points:2
Priority:
M
Story ID: 29

## Slide 19: Mall information
As a user, I want to browse information about malls so that I can find out which malls offer the most ideal shopping experience.
Acceptance Criteria:
Users can click on a ‘Malls’ link, which directs the users to the ‘Malls’ page.
Users can see the name, address, phone number, and email address of every mall in the city.
The system provides a map that pinpoints the location of every zoo.
Clicking on ‘Brands’ displays a list of brands that the mall sells.
Notes:
Story Points:2
Priority:
M
Story ID: 30

## Slide 20: Specialised Information
Users can view information that is more specialised that City-based information. Registered users are given recommendations based on their demographic. However, access to specialised information isn’t limited to its intended account type.

## Slide 21: Hotel infomation for tourists
As a tourist, I want to be able to view information about hotels so that I can find the most ideal accommodation while staying in Australia.
Acceptance Criteria:
A link ‘Hotels‘ is displayed in the menu for user type ‘Tourist‘.
Clicking ‘Hotels‘ displays the names, addresses, phone numbers and email addresses of all the hotels in the city.
A map of the city is displayed, pinpointing the locations of all the hotels.
Clicking on ‘Back‘ redirects the user to the menu.
Notes: Ideally, the system should provide this information for several Australian cities, not just for Brisbane.
Story Points:4
Priority:
M
Story ID: 8

## Slide 22: College information for students
As a student, I want to be able to view information about colleges so that I can find the most ideal colleges in my city.
Acceptance Criteria:
A link ‘Colleges‘ is displayed for students.
Clicking ‘Colleges‘ redirects the user to the list of names, addresses, departments and email addresses of the colleges in the city.
A city map is provided which contains marked locations for each of the colleges in the city.
Clicking on ‘Back‘ redirects the user to the main menu.
Notes:
Story Points:4
Priority:
M
Story ID: 9

## Slide 23: Library information for students
As a student, I want to be able to view information about libraries so that I can find the most ideal place to borrow books.
Acceptance Criteria:
A link ‘Libraries‘ is displayed in the menu for students.
Clicking ‘Libraries‘ displays the names, addresses, phone numbers and email addresses of the libraries in the city.
The system displays a map of the city that pinpoints the locations of all the libraries in the city.
The system provides a ‘Back‘ button that redirects the user to the menu.
Notes:
Story Points:4
Priority:
M
Story ID: 10

## Slide 24: Hotel information for businessmen
As a businessman, I want to be able to view hotel information so that I can conveniently find hotels when travelling for business.
Acceptance Criteria:
A link ‘Hotels‘ is displayed in the menu for businessmen users.
Clicking on the ‘Hotels‘ link redirects the user to the list of names, addresses, phone numbers and email addresses of the hotels in the city.
A map of the city is displayed, including the marked locations of the hotels in the city.
Clicking on ‘Back‘ redirects the user to the menu.
Notes:
Story Points:4
Priority:
M
Story ID: 11

## Slide 25: Industry information for businessmen
As a businessman, I want to be able to view information about industries so that I can evaluate industry data for my business.
Acceptance Criteria:
A link ‘Industries‘ should be displayed in the menu for businessmen users.
Clicking on ‘Industries‘ displays the names, addresses, industry types and email addresses of the common industries in the city.
The system provides a ‘Back‘ button that redirects the user to the menu.
Notes:
Story Points:4
Priority:
M
Story ID: 12

## Slide 26: Release 2
Delivery date: To be Discussed
Total Story Points: 59
This release will provide more granular features to the Smart City service. Users will be able to book sightseeing tickets with third party services, and bookmark certain entries. Weather forecasts will be available to users. Information will be categorised to allow entries for more than one city. The web application will be optimised for mobile use, and available in multiple languages. Users will be able to recover lost accounts, and auto-fill failed login forms. Users will be able to browse public transport services, student accommodation and current events similarly to the previously implemented types of entries. Users, registered or otherwise, will also be given easy access to emergency information & online emergency reporting.

## Slide 27: Extended Functionality
Users are provided with links to book tickets from third party sites. Users can view current temperature and other forecast data. When viewing an entry, users are given the option to view travel instructions to that entries location. Information entries can be categorised into city groups by system administrators, and users can narrow their searches down to a specific city.

## Slide 28: Travel directions
As a user, I want the website to display the directions to the destination so that I can find the most direct routes when travelling around the city.
Acceptance Criteria:
User input fields are provided for the starting point and destination.
There are 3 options: walking, taking a bus/train, and driving.
Clicking an option displays the most direct route for that method of transport.
The total distance is displayed in metres.
The system estimates the total travel time in hours and minutes.
Clicking on ‘Print’ opens the print dialog window to offer me to print the city map (with the directions).
Notes:
Story Points:8
Priority:
S
Story ID: 23

## Slide 29: Weather forecast
As a user, I want the system to display weather forecasts so that I can anticipate the weather conditions when I travel around the city.
Acceptance Criteria:
The system displays the forecasted temperature (min/max), the type of weather (sunny, cloudy, rainy, or stormy), precipitation, humidity and wind speeds of the city.
The weather forecast changes accordingly when the user chooses a different city.
Notes:
Story Points:4
Priority:
C
Story ID: 17

## Slide 30: Book sightseeing tickets
As a tourist, I want the system to book sightseeing tickets so that I do not need to spend more time finding where to book tickets.
Acceptance Criteria:
Users can see the price for each sightseeing ticket
Users can see the name, dates, and activities of each tour.
Clicking on ‘Register’ redirects the user to the corresponding booking website.
Notes:
Story Points:4
Priority:
C
Story ID: 24

## Slide 31: Information for other cities
As a user, I want the system to account for different Australian cities so that I can still utilise the system if I move to another city.
Acceptance Criteria:
A ‘Change city‘ link is provided
Clicking ‘Change city‘ displays a drop down menu of the cities that the user can choose from (to gain information about that particular city).
The system contains the names, addresses, phone numbers/departments/industry types, and email addresses of the hotels, cities (parks, zoos, museums, malls, and restaurants), colleges, libraries, and industries for different cities across Australia.
Notes:
Story Points:4
Priority:
S
Story ID: 5

## Slide 32: Usability Features
Users can switch the language of the web application. User experience is optimised for mobile browsing as well as browsing on PC. Users can bookmark specific entries to allow quick return. Information entry forms fill automatically on failed logins / registrations. User accounts with lost passwords can be recovered by contacting user email / phone no.

## Slide 33: Language settings
As a user, I want the system to be translated into other languages so that I can understand the information clearly.
Acceptance Criteria:
Links for different languages are provided at the bottom of the page.
Clicking a language should translate all the information in the system into the chosen language.
Notes:
Story Points:8
Priority:
S
Story ID: 15

## Slide 34: Filling forms automatically
As a user, I want the system to fill the information I have entered automatically so that I do not have to input the same data again.
Acceptance Criteria:
The system stores a record of user-inputted data into a database.
All user input fields can be filled in automatically based on the user’s previous inputs.
Notes:
Story Points:1
Priority:
S
Story ID: 25

## Slide 35: Mobile optimisation
As a user, I want the website to be optimised for phones so that I can utilise the system more effectively while I am travelling.
Acceptance Criteria:
Phone users can have two options of using the website: ‘View computer mode’ or ‘View phone mode’.
‘View computer mode’ is set by default.
Clicking ‘View phone mode’ resizes the website and optimises the display for phone users.
Notes:
Story Points:8
Priority:
S
Story ID: 21

## Slide 36: Bookmarks
As a user, I want the website to have bookmarks so that I can save time when searching for information.
Acceptance Criteria:
A bookmark icon is displayed for each type of information.
Clicking on the bookmark icon creates a listing on the ‘Bookmarks’ page.
Clicking the ‘Bookmarks’ page displays a list of the bookmarked information.
Clicking on a bookmark redirects the user to the corresponding page.
Right-clicking a bookmark deletes the bookmark.
Notes:
Story Points:4
Priority:
C
Story ID: 22

## Slide 37: Account Recovery
As a user, I want the website to have an account recovery system so that I can recover my account if I lose my password.
Acceptance Criteria:
A link ‘Forgot your password?‘ is be displayed.
Clicking ‘Forgot your password?‘ displays two options that the user can choose from (send a recovery email or send a recovery text message).
Clicking ‘Ok‘ after selecting an option should send a recovery link that allows the user to enter a new password.
Clicking ‘Confirm‘ should effectively change the user‘s password, and should redirect the user to a confirmation page.
Notes:
Story Points:4
Priority:
S
Story ID: 13

## Slide 38: Public transport services
As a user, I want to know the options for public transport so that I can find the most convenient methods of travelling around the city.
Acceptance Criteria:
A link ‘Public transport‘ is be displayed for all users.
Clicking ‘Public transport‘ should display the list of names, routes, email addresses, and phone numbers for the city bus and metro rail services in the city.
A map of the city should be provided, outlining the routes for the city bus and metro rail.
Clicking the ‘Back‘ button should redirect the user to the main menu.
Notes:
Story Points:4
Priority:
C
Story ID: 14

## Slide 39: Additional Information Types
Users can view more types of city information, using the search bar functionality implemented in Release 1. Emergency information is easily accessible by all kinds of users, registered or otherwise.

## Slide 40: Student accommodation
As a student, I want a list of student accommodation so that I can find a place to rent out while I study.
Acceptance Criteria:
A link ‘Accommodation’ is displayed for student users.
Clicking ‘Accommodation’ displays a list of the names, locations, contact details and prices of trusted student accommodation in the city.
Links are provided for rental websites and student accommodation websites.
Clicking on ‘Back’ redirects the user to the menu.
Notes:
Story Points:4
Priority:
C
Story ID: 18

## Slide 41: Event information
As a tourist, I want the system to provide an event calendar so that I find events to attend during my vacation.
Acceptance Criteria:
A link ‘Events’ is provided for Tourist users.
Clicking ‘Events’ displays a list of events. Including the date, time and location of the event, and a simple description of the event.
The events are ordered by date.
Clicking ‘Location’ displays the location of the event on the city map.
Clicking an event redirects the user to the website associated with the event.
Clicking on ‘Back’ redirects the user to the menu.
Notes:
Story Points:4
Priority:
C
Story ID: 19

## Slide 42: Emergency information
As a user, I want to know emergency contact details so that I can call for help if an accident occurs.
Acceptance Criteria:
A list of names and numbers are provided for emergencies.
The system displays the locations, contact details, and opening hours for the hospitals in the city.
Notes:
Story Points:2
Priority:
C
Story ID: 20