## Sheet1
SPRINT 1
| total hours |  | 46 | Release 1 - Basic Functionality
days | total estimated hours left | estimated hours completed | expected hours completed | Date | Notes
1 | 46 | 2 | 46 | 2017-08-28 | First Django Application Implementation (actually 23/08/2017)
2 | 44 |  | 44.2 | 2017-08-29
3 | 44 |  | 42.4 | 2017-08-30
4 | 44 |  | 40.6 | 2017-08-31
5 | 44 |  | 38.8 | 2017-09-01
6 | 44 |  | 37 | 2017-09-02
7 | 44 |  | 35.2 | 2017-09-03
8 | 44 |  | 33.4 | 2017-09-04
9 | 44 |  | 31.6 | 2017-09-05
10 | 44 | 2 | 29.8 | 2017-09-06 | Database design drafted
11 | 42 | 1 | 28 | 2017-09-07 | First Django Database implementation
12 | 41 |  | 26.2 | 2017-09-08
13 | 41 |  | 24.4 | 2017-09-09
14 | 41 | 4 | 22.6 | 2017-09-10 | Log in, Register UI Designs finished
15 | 37 | 2 | 20.8 | 2017-09-11 | CSS Stylesheet finalised
16 | 35 |  | 19 | 2017-09-12
17 | 35 |  | 17.2 | 2017-09-13
18 | 35 |  | 15.4 | 2017-09-14
19 | 35 | 7 | 13.6 | 2017-09-15 | Django superuser created, pages coded to perform admin tasks
20 | 28 | 4 | 11.8 | 2017-09-16 | Acceptance testing (admin)
21 | 24 | 4 | 10 | 2017-09-17 | Official database ERD designed, implemented
22 | 20 | 4.5 | 8.2 | 2017-09-18 | Homepage, Settings designs finished
23 | 15.5 | 2 | 6.4 | 2017-09-19 | HTML implementations added to Django, city-based views working
24 | 13.5 | 5.5 | 4.6 | 2017-09-20 | index page implemented to show all city data
25 | 8 | 6 | 2.8 | 2017-09-21 | Acceptance testing (index)
26 | 2 |  | 1 | 2017-09-22